## Works_EN
tag | title | subtitle | category | funded by | approved | included in a programme | open to assignment | assigned | completion | responsible agency | private actor involved | announced budget | indicative completion timeframe in months | indicative start date | indicative end date | exact start date | exact end date | real duration in months | latest update | budget different than announced | furthered timeframe | description | location-area of implementation | comments
A1 | New Main Road Axis, North Evia Spine (Psachna – Strofylia section) |  | Infrastructure | National Infrastructure Development Program | yes | no | no | no | no | Ministry of Infrastructure & Transport |  | 230000000 | 67 | 2024-06-01 | 2029-12-31 | 2025-11-25 |  |  | 2025-11-30 |  |  | Following the invitation of the Ministry of Infrastructure and Transport to the Region of Central Greece to submit a proposal for the preparation of the necessary studies for the first section of the northern road axis from Psachna to Strofyllia, the Region submitted the complete dossier on 25 November 2025, including the technical data sheets, supporting documentation and tender documents for the relevant studies. The submission deadline was 31 December 2025. The proposal is now pending evaluation by the competent authority, after which approval is expected, followed immediately by tendering. |  | https://pste.gov.gr/deltio-typou-o-perifereiarchis-stereas-elladas-fanis-spanos-eiche-synantisi-ergasias-me-ton-ypourgo-ypodomon-metaforon-christo-dima-gia-tin-poreia-ylopoiisis-ergon-kai-meleton/
A2 | New Main Road Axis, North Evia Spine (Strofylia – Istiaia section) |  | Infrastructure | Regional Operational Program of Sterea Ellada 2014-2020 (ΠΕΠ 2014-2020) | yes | no | no | no | no | Region of Sterea Ellada |  | 1300000 | 73 | 2023-12-01 | 2029-12-31 |  |  |  | 2025-10-14 |  |  |  |  | The region of Sterea Ellada has included in its programme the funding for the necessary studies, up to the point of the procurement of the project. The temporarily assigned agent has though not yet been made public and funding for the project (studies, procurement, assignment) has not been found.
A3 | New branches of the New Main Road Axis towards coastal zones |  | Infrastructure | Regional Operational Program of Sterea Ellada 2014-2020 (ΠΕΠ 2014-2020) | yes | no | no | no | no | Region of Sterea Ellada |  | 1000000 | 1 | 2023-12-01 | 2023-12-31 |  |  |  | 2025-10-14 |  |  |  |  | The region of Sterea Ellada has included in its programme the funding for the necessary studies, up to the point of the procurement of the project. The temporarily assigned agent has though not yet been made public and funding for the project (studies, procurement, assignment) has not been found.
A4 | Superfast North Evia, support for businesses and households in Mantoudi, Limni, Agia Anna for upgrading internet connectivity |  | Infrastructure | Other | yes | no | no | no | no | Skapani A.E. |  | 200000 | 12 | 2023-01-01 | 2023-12-31 |  |  |  | 2025-10-14
B1 | Regeneration of settlements in the Municipality of Istiaia–Aidipsos |  | Infrastructure | Regional Program of Sterea Ellada 2021-2027 | yes | yes | no | no | no | Municipality of Istiaia-Aidipsos |  | 3000000 | 36 | 2025-01-01 | 2027-12-31 |  |  |  | 2025-12-16 |  |  |  |  | In search for funding.
A5 | APOLIPSIS programme |  | Forest | Green Fund | yes | yes | yes | yes | yes | General Forestry Administration |  | 30000 | 13 | 2022-06-01 | 2023-06-30 |  |  |  | 2025-09-25 |  |  | Creation of digital platform for the information of the citizens regarding the logging and the collection of the burnt trees of the area | Municipalities of Istiaia-Aidipsos & Limni-Mantoudi-Agia Anna
A6 | Restoration of infrastructures in forest recreation areas |  | Forest | Green Fund | yes | yes | yes | yes | yes | General Forestry Administration (Γενική Γραμματεία Δασών) |  | 381920 | 8 | 2022-10-01 | 2023-05-31 |  |  |  | 2025-09-25 |  |  | These areas were built by the Limni Forest Service over a period of about 15 years and now require urgent restoration after suffering damage in the devastating 2021 wildfires in northern Evia. Their rehabilitation will also improve their appearance and functionality, provide safe and attractive recreation spaces for visitors, support environmental education, and help boost tourism and the local economy without harming the natural environment. | Χώρος δασικής αναψυχής «Καταρράκτες Δρυμώνα»-Μονοπάτι Ξηρόν Όρος» Περιηγητικές διαδρομές πέριξ του Δασικού Χωριού «Παπάδες» (πράσινη διαδρομή-κόκκινη διαδρομή) Χώρος δασικής αναψυχής «Βαθύρεμα-Ταμπακαριά-Προφήτης Ηλίας» Μονοπάτι «Καναλάκια-Χριστός-Άγιος Γρηγόριος-Μεσοπέτρι» Χώρος δασικής αναψυχής «Καμαρίτσα»-Μονοπάτι προς όρος Καβαλάρη | A study for the project had already been made and approved by the Forestry Directorate of Evia
A7 | Maintenance, signage and promotion of marked hiking routes in the Istiaia–Aidipsos municipality area |  | Forest | Recovery & Resilience Plan | yes | yes | yes | no | no | Municipality of Istiaia-Adipsos |  | 304800 | 12 | 2022-11-01 | 2023-10-31 |  |  |  | 2025-09-25 | 99695 | 2025 | The project aims to attract visitors from Greece and abroad to the Municipality of Istiaia-Edipsos who are interested in alternative forms of tourism such as hiking and mountaineering. The routes run through mountainous, rural, and less tourist-developed areas away from the busy coastal zone, with the goal of strengthening the local economies of the small villages in these regions. | Municipalities of Istiaia-Aidipsos | equivalent works for Mantoudi Agia Anna were approved by the same formal approval and are actually referred in A9
A8 | Hydrological study for mountain and lowland works in North Evia |  | Forest | Regional Development Program 2021-2025 | yes | yes | yes | yes | yes | Sterea Ellada region | Civil engineer_Charampos Afrataios | 30000 | 6 | 2022-10-01 | 2023-03-31 |  |  |  | 2025-09-25 |  |  | The project achieves the following: it records all water supply and irrigation needs of the two municipalities of northern Euboea; assesses the volume of water that existing technical excavations from magnesite mining can collect so they may be used as permanent reservoirs; and identifies all sites proposed to date for the construction of water storage dams together with their storage capacities. It also supports the efficient organization of water resources and the preparation of a water management programme with a corresponding timetable, while integrating all previous actions in this field into a coherent and unified water policy. | Municipalities of Istiaia-Aidipsos & Limni-Mantoudi-Agia Anna | It is a study, not construction works are made with this
A9 | National Trail 21 in Evia |  | Forest | Recovery & Resilience Plan | yes | yes | yes | no | no |  |  | 125860 | 9 | 2024-02-01 | 2024-10-31 |  |  |  | 2025-09-25 | 326199.82 | 2025 |  |  | Η μελέτη του έργου έχει ολοκληρωθεί από το Σωματείο “ΔΙΑΖΩΜΑ” και ήδη έχει προσφερθεί ως δωρεά στο Δήμο Μαντουδίου – Λίμνης – Αγ. Άννας.
A10 | Non-public forestry programme |  | Forest | Other | yes | no | no | no | no | General Forestry Administration (Γενική Γραμματεία Δασών) | Owners of non-public forests and forested areas | 1200000 | 56 | 2023-05-01 | 2027-12-31 |  |  |  | 2025-10-14
A11 | Reconstruction of the Papades forest village infrastructure destroyed by the 3 Aug 2021 fire |  | Forest | National Development Program 2021-2025 | yes | yes | yes | yes | yes | Forestry Office of Limni |  | 780000 | 10 | 2022-10-01 | 2023-07-31 |  |  |  | 2025-09-25
A12 | Prevention_Forest protection, Goldammer Committee report, Actions for the mobilisation of the local communities |  | Forest | Other | yes | no | no | no | no | Ministry of Environment and Energy |  | 455000 | 1 | 2023-12-01 | 2023-12-31 |  |  |  | 2025-10-14 |  |  |  |  | The project covers the actions that must be taken before the fire season to reduce the likelihood of wildfires, make them easier to contain, limit potential damage in the event of a major fire, and improve the organization and preparedness of the authorities involved for the immediate response to such incidents. Funding is now being sought for the implementation of the programme.
A13 | Forest economy | A_Establishment of the prototype Social Cooperative Enterprise with the distinctive title 'Sustainability' | Forest | Donations | yes | yes | yes | yes | no | University of Thessaly, Union of social and economic solidarity bodies in Sterea Ellada | Legal support of Sotiris Fwteas, president of Diazoma | 40000 | 12 | [5 empty] | 2025-10-14 |  |  |  |  | Modification of legislation is necessary for the continuation of this project, Law 5106/2024-Article 20,par3 is mentioned
A14 |  | B_Protection of Greek forests and use / exploitation of forest products | Forest | Other | yes | no | no | no | no | Ministry of Environment and Energy, University of Thessaly, Forestry office of Istiaia, Forestry office of Limni |  | 540000 | 12 | [5 empty] | 2025-10-14
A15 | Reforestation | A_Collection and handling of the forest forest reproductive material | Forest | Recovery & Resilience Plan | yes | yes | yes | yes | yes | Ministry of Environment and Energy, General Forestry Administration, A.U.Th. |  | 70000 | 18 | 2023-07-01 | 2024-12-31 |  |  |  | 2025-10-14
A16 |  | B_Production of nursery seedlings for reforestation | Forest | Recovery & Resilience Plan | yes | yes | yes | yes | no | Ministry of Environment and Energy, General Forestry Administration, A.U.Th. |  | 600000 | 36 | 2024-01-01 | 2026-12-31 |  |  |  | 2025-10-14
A17 |  | C_Observation of the natural regeneration of the 'New Forest' | Forest | Donations | yes | yes | yes | yes | no | A.U.Th. |  | 85000 | 48 | 2024-01-01 | 2027-12-31 |  |  |  | 2025-10-14
A18 |  | D_Reforestation, Sustainable management and cleaning | Forest | Recovery & Resilience Plan | yes | yes | yes | yes | no | Ministry of Environment and Energy, General Forestry Administration, A.U.Th. |  | 16580000 | 48 | 2024-01-01 | 2027-12-31 |  |  |  | 2025-10-15
A19 |  | E_ Works for the restoration of the soil moisture | Forest | Other | yes | yes | yes | no | no | Ministry of Environment and Energy, General Forestry Administration, A.U.Th. |  | 3150000 | 36 | 2024-01-01 | 2026-12-31 |  |  |  | 2025-10-14
A20 |  | F_ Calculation and monitoring of CO₂ and carbon absorption | Forest | Donations | yes | yes | yes | no | no | Ministry of Environment and Energy, General Forestry Administration, A.U.Th. |  | 130000 | 36 | 2024-01-01 | 2026-12-31 |  |  |  | 2025-10-14
A21 | Training and upskilling actions for the local population |  | Agrifood sector | Donations | yes | yes | yes | yes | yes | American Farm School | American Farm School | 35000 | 12 | 2022-07-01 | 2023-06-30 |  |  |  | 2025-10-14 |  |  | The aim of this action is to cover the new needs that arose after the wildfires of 2021 and to support the local farmers and producers through counselling, new knowledge and skills
A22 | Training for workers in catering and leisure |  | Agrifood sector | Other | yes | no | no | no | no |  |  |  | 48 | 2023-01-01 | 2026-12-31 |  |  |  | 2025-10-14 |  |  | This project was implemented with funding from other sources, both from the state and the Regional Government, and is excluded from the Reconstruction of Evia program.
A23 | Supply chains |  | Agrifood sector | Regional Program of Sterea Ellada 2021-2027 | yes | no | no | no | no | ΣΚΑΠΑΝΗ Α.Ε. |  | 500000 | 48 | 2023-01-01 | 2026-12-31 |  |  |  | 2025-10-14 |  |  | This action is supposed to be financed by the action B2_"Investing in North Evia - Support for existing small and very small businesses in the agri-food chain in North Evia" which has been approved within the framework of the O.X.E. of North Evia, in order to ensure unified implementation and better coordination of actions. |  | LINK TO B2, presented as different actions but in reality is one programme.
A24 | Open Shelf |  | Agrifood sector | Regional Program of Sterea Ellada 2021-2027 | yes | no | no | no | no | ΣΚΑΠΑΝΗ Α.Ε. |  | 500000 | 48 | 2023-01-01 | 2026-12-31 |  |  |  | 2025-10-14 |  |  | This action is supposed to be financed by the action B2_"Investing in North Evia - Support for existing small and very small businesses in the agri-food chain in North Evia" which has been approved within the framework of the O.X.E. of North Evia, in order to ensure unified implementation and better coordination of actions. |  | LINK TO B2, presented as different actions but in reality is one programme.
B2 | Invest in North Evia – support for existing small and very small agrifood-chain businesses in North Evia |  | Agrifood sector | Regional Program of Sterea Ellada 2021-2027 | yes | yes | no | no | no | Municipality of Istiaia-Adipsos, Municipality of Limni-Mantoudi-Agia Anna |  | 1000000 | 36 | 2025-01-01 | 2027-12-31 |  |  |  | 2025-12-16
A25 | Livestock support – livestock facilities |  | Agrifood sector | Rural Development Programme | yes | no | no | no | no | Ministry of Agricultural Development & Food |  | 480000 | 36 | 2023-01-01 | 2025-12-31 |  |  |  | 2025-10-14 |  |  | Provision of housing infrastructure for livestock facilities serving 25% of the existing livestock farmers in Northern Evia. | Rovies | smart agriculture
A26 | Istiaia Beekeeping School / beekeeping seminars |  | Agrifood sector | Sectoral Development Program of the Ministry of Education 2021-2025 | yes | no | no | no | no | Ministry of Agricultural Development & Food, Ministry of Education & Religion |  | 200000 | 12 | 2025-01-01 | 2025-12-31 |  |  |  | 2025-10-14
A27 | Installation of a smart agriculture system in the Rovies cooperative |  | Agrifood sector | Regional Development Program 2021-2025 | yes | yes | yes | yes | yes | Rovies cooperative |  | 40000 | 1 | 2022-12-01 | 2022-12-31 |  |  |  | 2025-10-14
A28 | Creation of prototype public forest apiaries |  | Agrifood sector | Donations | yes | yes | yes | yes | yes |  |  | 45000 | 1 | 2023-06-01 | 2023-06-30 |  |  |  | 2025-09-25
A29 | North Evia agricultural products exhibition – Syntagma Metro |  | Agrifood sector | Donations | yes | yes | yes | yes | yes |  |  | 20000 | 1 | 2023-01-07 | 2023-01-09 |  |  |  | 2025-09-25
A30 | Grant support for existing businesses affected by the pandemic in areas hit by major natural disasters |  | Human Resources | Competitiveness Programme 2021-2027 | yes | yes | yes | yes | yes | Intermediate Body for the Management of Operational Programmes. |  | 26000000 | 6 | [5 empty] | 2025-10-14
A31 | Special employment programme for a) resin workers and b) graduates of higher education institutions in services of the Ministry of Environment and Energy |  | Human Resources | National Employment Service (Δ.ΥΠ.Α) | yes | yes | yes | yes | no |  |  | 63000000 | 120 | 2022-01-01 | 2031-12-31 |  |  |  | 2025-10-14
A32 | Pre-employment programme for 300 unemployed young people aged 18–30 in private-sector businesses and public-sector entities with regular economic activity in the municipalities of Istiaia–Aidipsos and Mantoudi–Limni–Agia Anna |  | Human Resources | National Employment Service (Δ.ΥΠ.Α) | yes | yes | yes | yes | yes |  |  | 20000000 | [6 empty] | 2025-10-14 |  |  |  |  | Marked as COMPLETED
A33 | POLITIS programme infrastructure: creation of a Spatial Planning and Environment Centre (KECHOP), a holistic multi-purpose Citizen Service Centre (KEP), and space for the intermunicipal development organisation (DMO) in Istiaia, plus a new KEP with a community clinic in Vasilika |  | Human Resources | Other | yes | no | no | no | no | Diazoma,Municipality of Istiaia-Aidipsos | Arxikon A.E., Papagannis have submitted the studies that were donated by Diazoma | 1413000 | 20 | [5 empty] | 2025-10-14
A34 | POLITIS programme infrastructure: creation of a Citizen Service Centre (KEP) and a Spatial Planning and Environment Centre (KECHOP) in Mantoudi, plus a KEP in Agia Anna |  | Human Resources | Other | yes | no | no | no | no | Diazoma,Municipality of Limni-Mantoudi-Agia Anna | Arxikon A.E., Papagannis have submitted the studies that were donated by Diazoma | 768000 | 20 | [5 empty] | 2025-10-14
A35 | Digital applications – “POLITIS” programme (upgrade of the KEP information system) |  | Human Resources | Good Governance - Institutions and Transparency / EEA Grants 2014–2021 | yes | yes | yes | yes | yes | Ministry of Digital Governance |  | 1360000 | 2 | 2024-02-01 | 2024-03-31 |  |  |  | 2025-09-25
A36 | Digital applications – “POLITIS” programme (municipal geospatial information geoportal and codification of environmental legislation – Municipality of Aidipsos) |  | Human Resources | Donations | yes | no | no | no | no | Municipality of Istiaia-Aidipsos |  | 65000 | 12 | 2023-01-01 | 2023-12-31 |  |  |  | 2025-10-14
A37 | Digital applications – “POLITIS” programme (municipal geospatial information geoportal and codification of environmental legislation – Municipality of Limni) |  | Human Resources | Donations | yes | no | no | no | no | Municipality of Limni-Mantoudi-Agia Anna |  | 65000 | 12 | 2023-01-01 | 2023-12-31 |  |  |  | 2025-10-14
A38 | Digital applications – “POLITIS” programme (Digital Observatory for Sustainable Tourism Development DataHub) – Municipality of Istiaia |  | Human Resources | Donations | yes | no | no | no | no | Municipality of Istiaia-Aidipsos |  | 85000 | 12 | 2023-01-01 | 2023-12-31 |  |  |  | 2025-10-14
A39 | Study for establishing an Energy Community for the municipalities of Mantoudi–Limni–Agia Anna and Istiaia–Aidipsos |  | Human Resources | Green Fund | yes | yes | yes | yes | no | Municipality of Limni-Mantoudi-Agia Anna |  | 70000 | 1 | 2023-01-31 | 2023-01-31 |  |  |  | 2025-10-14
A40 | Procurement of one (1) 4x4 ambulance vehicle for the Istiaia Health Centre |  | Healthcare & Welfare | National Development Program 2021-2025 | yes | yes | yes | no | no |  |  | 100000 | 8 | [5 empty] | 2025-11-06 | 113646 |  |  |  | To be completed by the end of 2026
A41 | Procurement of medical equipment for the needs of the Istiaia Health Centre (including a chronic patients centre) |  | Healthcare & Welfare | National Development Program 2021-2025 | yes | yes | yes | yes | no |  |  | 554000 | 8 | [5 empty] | 2025-11-06 |  |  |  |  | The remaining administrative procedures have to be completed in order for the work to be completed.
A42 | Procurement of medical equipment for the needs of the Mantoudi Health Centre |  | Healthcare & Welfare | National Development Program 2021-2025 | yes | yes | yes | yes | yes |  |  | 16155 | 8 | [5 empty] | 2025-09-25 |  |  |  |  | Completed
A43 | Procurement of one mobile gynaecological unit for the population of North Evia |  | Healthcare & Welfare | National Development Program 2021-2025 | yes | yes | yes | yes | no |  |  | 290000 | 8 | [5 empty] | 2025-09-25 |  |  |  |  | There is a contract already, the completion of the work is awaited.
A44 | Procurement of one mobile blood collection unit |  | Healthcare & Welfare | National Development Program 2021-2025 | yes | yes | yes | yes | no |  |  | 290000 | 8 | [5 empty] | 2025-09-25 |  |  |  |  | There is a contract already, the completion of the work is awaited.
A45 | Preventive medicine – outreach and information actions at various points in North Evia |  | Healthcare & Welfare | Other | yes | no | no | no | no | Skapani A.E. |  | 125000 | 12 | 2023-01-01 | 2023-12-31 |  |  |  | 2025-09-25 |  |  |  |  | Awaiting funding
A46 | Tele-counselling – pilot use of the existing inactive platform for: a) Covid, b) child and adolescent mental health, extended to chronic patient care and the personal doctor |  | Healthcare & Welfare | Other | yes | no | no | no | no | e-Government for Health and Social Security |  | 300000 | 24 | 2023-01-01 | 2024-12-31 |  |  |  | 2025-09-25
A47 | Creation of a needs map for health and welfare networks within the framework of North Evia reconstruction |  | Healthcare & Welfare | Donations | yes | yes | yes | yes | yes | Diazoma | Diazoma | 20000 | 5 | 2022-11-01 | 2023-03-31 |  |  |  | 2025-09-25 |  |  |  |  | Awaiting the relevant call for proposals for the inclusion of the project’s funding in the Northern Euboea ITI (NSRF 2021–2027 ¦ Regional Operational Programme of Central Greece).
B3 | Strengthening social care, protection and inclusion: “First Hug” |  | Healthcare & Welfare | Regional Program of Sterea Ellada 2021-2027 | yes | yes | no | no | no | Municipality of Istiaia-Aidipsos, Municipality of Limni-Mantoudi-Agia Anna |  | 1000000 | 36 | 2025-01-01 | 2027-12-31 |  |  |  | 2025-12-16
B4 | Strengthening social care, protection and inclusion: experiential culture workshops for adolescents |  | Healthcare & Welfare | Regional Program of Sterea Ellada 2021-2027 | yes | yes | no | no | no | Municipality of Istiaia-Aidipsos, Municipality of Limni-Mantoudi-Agia Anna |  | 700000 | 36 | 2025-01-01 | 2027-12-31 |  |  |  | 2025-12-16
B5 | Independent living for people in need in North Evia |  | Healthcare & Welfare | Regional Program of Sterea Ellada 2021-2027 | yes | yes | no | no | no | Municipality of Istiaia-Aidipsos, Municipality of Limni-Mantoudi-Agia Anna |  | 300000 | 36 | 2025-01-01 | 2027-12-31 |  |  |  | 2025-12-16
A48 | Reopening of the Aidipsos hydrotherapy centre_Management and distribution of the thermal resource of spa tourism in Aidipsos |  | Tourism | Other | yes | no | no | no | no | Public Properties Company |  | 500000 | 6 | [5 empty] | 2025-10-14 |  |  |  |  | In search for funding.
A49 | Touristic Promotion |  | Tourism | Other | yes | no | no | no | no | Skapani A.E. |  | 665000 | 36 | 2023-01-01 | 2025-12-31 |  |  |  | 2025-10-14
A50 | Installation of free Wi‑Fi points in the municipalities of Northern Evia |  | Tourism | Donations | yes | yes | yes | yes | yes | COSMOTE | COSMOTE | - | [6 empty] | 2025-09-25
AB51 | Upgrade of tourism spots-nodes_Agia Anna beach |  | Tourism | Regional Program of Sterea Ellada 2021-2027 | yes | yes | no | no | no | Municipality of Limni-Mantoudi-Agia Anna | Diazoma | 2500000 | 36 | 2025-01-01 | 2027-12-31 |  |  |  | 2025-12-16 |  |  | For the Agia Anna beachfront redevelopment project, the DIAZOMA Association commissioned a study, which was completed and submitted to the Municipality of Mantoudi–Limni–Agia Anna as a donation. Following the Municipality’s approval of the donation, the way is opened for the implementation of the project, which is included in the core group of projects under the Northern Euboea ITI (Regional Operational Programme of Central Greece).
AB52 | Upgrade of tourism spots-nodes_Rovies beach |  | Tourism | Regional Program of Sterea Ellada 2021-2027 | yes | yes | no | no | no | Municipality of Limni-Mantoudi-Agia Anna | Diazoma | 2500000 | 36 | 2025-01-01 | 2027-12-31 |  |  |  | 2025-12-16 |  |  | accordingly
A53 | Blue Flags |  | Tourism | OFYPEKA | yes | yes | yes | no | no | Municipality of Istiaia-Aidipsos, Municipality of Limni-Mantoudi-Agia Anna |  | 228000 | 12 | 2023-01-01 | 2023-12-31 |  |  |  | 2025-09-25
A54 | Education – training – support for professionals of the touristic sector and the local population |  | Tourism | Competitiveness Programme 2021-2027 | yes | no | no | no | no | Skapani A.E. |  | 400000 | 48 | 2023-01-01 | 2026-12-31 |  |  |  | 2025-09-25 |  |  | The project is currently under specification by the Ministry of Development and Investments through the Competitiveness Programme 2021–2027
A55 | Reopening of the Aidipsos hydrotherapy centre_ Redevelopment of the surrounding area of the centre |  | Tourism | Other | yes | yes | yes | yes | no | Municipality of Istiaia-Aidipsos | AEGEAS Civil Non-Profit Organization for Cultural and Public-Benefit Activities. | 70000 | 60 | 2023-01-01 | 2027-12-31 |  |  |  | 2025-10-14 |  |  | A multidisciplinary team was commissioned to prepare a Strategic Study – Master Plan entitled “Edipsos Baths ‘META’: Strategic Master Plan for Enhancement, Protection and Reconstruction,” funded through a €70,000 donation from AEGEAS AMKE to the Municipality of Istiaia–Edipsos. The completed Strategic Study – Master Plan proposes the commissioning of five (5) studies for the redevelopment of the surrounding area. | Aidipsos | Integrated to B.6.
A56 | Museum exhibition in Oreoi |  | Culture | Regional Program of Sterea Ellada 2021-2027 | yes | no | no | no | no | Municipality of Istiaia-Aidipsos, Ministry of Culture |  | 100000 | 48 | 2024-01-01 | 2027-12-31 |  |  |  | 2025-10-31 |  |  | This specific project is being integrated with the ‘Historical Information Center / Exhibition Space of Oreoi,’ which has been approved within the framework of the Northern Evia I.T.I., in order to ensure unified implementation and better coordination of the actions
B6 | Historical information centre / exhibition space in Oreoi |  | Culture | Regional Program of Sterea Ellada 2021-2027 | yes | yes | no | no | no | Municipality of Istiaia-Aidipsos |  | 2000000 | 36 | 2025-01-01 | 2027-12-31 |  |  |  | 2025-12-16
A57 | Petrified Forest – Kerasia annex |  | Culture | Green Fund | yes | yes | yes | yes | no | Natural History Museum of the Lesvos Petrified Forest |  | 637740 | 1 | 2022-02-01 | 2022-02-28 |  |  |  | 2025-09-25
A58 | Agioi Anargyroi building – Museum of North Evia |  | Culture | Other | yes | no | no | no | no | Ministry of Culture |  | 40000 | 48 | 2024-01-01 | 2027-12-31 |  |  |  | 2025-10-14 |  |  |  | Aidipsos | The study for the restoration of the building of Agioi Anarguroi by Ernst Ziller is yet to be assigned after funding is found for the project.
A59 | Archaeological excavation at Kastri of Kirinthos |  | Culture | National Development Program 2021-2025 | yes | yes | yes | yes | no | Ministry of Culture, Archaeological Agency of Evia |  | 216000 |  |  |  | 2022-10-01 |  |  | 2025-11-06 |  |  | The purpose of the project is the excavation and enhancement of the archaeological site at Kastri, Kirinthos, with the expected outcomes of promoting and highlighting the area’s cultural heritage, increasing visitation for cultural and research purposes, and further advancing the science of archaeology. | Kirinthos | ongoing
A60 | Restoration of the listed historic monument “Konaki” in Kechries, Evia |  | Culture | PEKA (former YMEPERAA) | yes | yes | yes | yes | no | Skapani A.E. |  | 1650000 | 24 | 2023-01-01 | 2024-12-31 |  |  |  | 2025-09-25 |  |  | The aim is to restore the “Konaki” building and convert it into a cultural centre that, beyond its aesthetic enhancement, will become functional and accessible, for the benefit of both residents and visitors. | Kexries | Works are to begin in summer 2026.
A61 | Restoration of the Church of Taxiarchon in Kokkinomilia, North Evia |  | Culture | Donations | yes | yes | yes | yes | no |  |  | 700000 | 24 | 2022-01-01 | 2023-12-31 |  |  |  | 2025-09-25 |  |  |  |  | Works are ongoing.
A62 | Architectural heritage networks of North Evia |  | Culture | Other | yes | no | no | no | no |  |  | 30000 | 13 | 2022-12-01 | 2023-12-31 |  |  |  | 2025-10-14 |  |  | In the search for funding for a study that would record and document the historic building stock of Northern Evia. The aim of this would be to recognise the architectural and historical heritage of the area and information of the local community and visitors. |  | In the search for funding.
A63 | Creation of a film hub for idea exchange and film market focused on the environment, titled “Evia Film Project” – Thessaloniki International Film Festival |  | Culture | Not defined | yes | yes | yes | yes | yes | Thessaloniki Film Festival |  | 260000 | 32 | 2023-03-01 | 2025-10-31 |  | 2025-12-31 |  | 2025-10-14 |  |  |  |  | Awaiting the decision of the Ministry of Culture for the continuation of the festival .
A64 | Educational, artistic and environmental action in two selected areas of N.Evia |  | Culture | Not defined | yes | yes | yes | yes | yes | Greek National Opera |  | 300000 | 32 | 2024-03-01 | 2026-10-31 |  | 2024-12-31 |  | 2025-10-14 |  |  |  | Limni, Kourkouloi
A65 | The 'Bridges of Music' |  | Culture | Not defined | yes | yes | yes | yes | yes | Athens Concert Hall |  | 100000 | 32 | 2023-03-01 | 2025-10-31 |  | 2025-12-31 |  | 2025-10-14
A66 | Cultural and sports events_local cultural capital |  | Culture | Other | yes | no | no | no | no |  |  |  | 37 | 2022-12-01 | 2025-12-31 |  |  |  | 2025-10-14 |  |  | This project was implemented with funding from other sources, both from the state and the Regional Government, and is excluded from the Reconstruction of Evia program.
A67 | Educational programme “We Support North Evia” |  | Culture | National Development Program 2021-2025 | yes | yes | yes | yes | yes | Ministry of Education |  | not defined | 24 | 2021-01-01 | 2022-12-31 |  |  |  | 2025-09-25
A68 | Forest festivals |  | Culture | Diazoma | yes | yes | yes | yes | yes | Diazoma |  | not defined | 36 | 2025-01-01 | 2027-12-31 |  |  |  | 2025-10-14
A69 | Training – awareness raising – mobilisation of professionals and the local population |  | Culture | Other | yes | no | no | no | no |  |  | 164875 | 37 | 2022-12-01 | 2025-12-31 |  |  |  | 2025-10-14 |  |  | This project was implemented with funding from other sources, both from the state and the Regional Government, and is excluded from the Reconstruction of Evia program. |  | The project supports 196 businesses in tourism, leisure and the creative industries, including 17 operating exclusively in the cultural and creative sectors. Indicative training topics: _Cultural resource management and use _Event organisation _Cultural marketing _Circular economy, construction and crafts _Culture and agri-food _Two programmes will be delivered: A) A 250-hour programme for 50 unemployed participants, including 150 hours of theory and 100 hours of practical training. B) A 150-hour programme for 25 employees, self-employed professionals and entrepreneurs in the cultural and creative sectors.
A70 | Design and development of innovative digital technology infrastructure and services for the reconstruction of North Evia |  | General | Other | yes | no | no | no | no | Skapani A.E. |  | 500000 | 48 | 2023-01-01 | 2026-12-31 |  |  |  | 2025-10-14 |  |  | This project was implemented with funding from other sources, both from the state and the Regional Government, and is excluded from the Reconstruction of Evia program.
A71 | Consulting, training and certification of North Evia human resources |  | General | Other | yes | no | no | no | no | Skapani A.E. |  | 1400000 | 48 | 2023-01-01 | 2026-12-31 |  |  |  | 2025-10-14 |  |  | This project was implemented with funding from other sources, both from the state and the Regional Government, and is excluded from the Reconstruction of Evia program.

## Programmes
Program Title | Total | EU | Greece | EU % | Greece % | website
National Infrastructure Development Programme
National Development Programme 2021-2025
Natural Environment & Climate Change Organization
Programme Environment & Climate Change | [5 empty] | https://peka-program.gr/
Regional Operational Program of Sterea Ellada 2014-2020 (ΠΕΠ 2014-2020) | 190052422 | 95026211 | 95026211 | 50% | 50% | https://2014-2020.espa.gr/el/Pages/staticOPStereaEllada.aspx
Regional Development Program 2021-2025
Green Fund | [5 empty] | https://prasinotameio.gr/organismos/skopos/
Regional Programme of Sterea Ellada 2021-2027 | 426052902 | 362156013 | 63909889 | 85% | 15% | https://www.espa.gr/el/Pages/staticPStereaEllada.aspx
Rural Development Programme 2014-2020 | 5880192246 | 4718291793 | 1161900453 | 80.24% | 19.76% | https://2014-2020.espa.gr/el/Pages/staticAgrotikiAnaptyxi.aspx
Rural Development Programme 2023-2027 | ??
Competitiveness 2021–2027 Programme | 382000000 | 310000000 |  | 81.15% | 0% | https://21-27.antagonistikotita.gr/en/programme-competitiveness/
Recovery & Resilience Plan
Sectoral Development Program of the Ministry of Education 2021-2025
Donations
Good Governance - Institutions and Transparency'_ European Economic Area Grants 2014-2021

## Works_GR
κωδικός | τίτλος | κατηγορία | χρηματοδότηση | έγκριση | ένταξη σε πρόγραμμα | ανοιχτό για ανάθεση | ανατέθηκε | ανατέθηκε σε (αν ιδιωτικός φορέας ολοκληρώνει το έργο) | υλοποίηση | ολοκλήρωση | προϋπολογισμός
A1 | ΝΕΟΣ ΟΔΙΚΟΣ ΑΞΟΝΑΣ – KOΡΜΟΣ ΒΟΡΕΙΑΣ ΕΥΒΟΙΑΣ: τμήμα Ψαχνά – Στροφυλιά | Υποδομές | Εθνικό Πρόγραμμα Ανάπτυξης (ΕΠΑ) Υποδομών | ναι | όχι | όχι |  |  | όχι | όχι
A2 | ΝΕΟΣ ΟΔΙΚΟΣ ΑΞΟΝΑΣ- KOΡΜΟΣ ΒΟΡΕΙΑΣ ΕΥΒΟΙΑΣ: τμήμα Στροφυλιά – Ιστιαία | Υποδομές | ΠΕΠ «Στερεά Ελλάδα 2014-2020» | ναι | όχι | όχι |  |  | όχι | όχι
A3 | Νέες διακλαδώσεις κεντρικού οδικού άξονα – κορμού Βόρειας Εύβοιας προς παράκτιες ζώνες | Υποδομές | ΠΕΠ «Στερεά Ελλάδα 2014-2020» | ναι | όχι | όχι |  |  | όχι | όχι
A4 | «Superfast North Evia» – Ενίσχυση επιχειρήσεων και νοικοκυριών της Δημοτικής Ενότητας Νηλέως του Δήμου Μαντουδίου – Λίμνης – Αγίας Άννας, για την αναβάθμιση της συνδεσιμότητάς τους στο διαδίκτυο | Υποδομές | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
B1 | Ανάπλαση οικισμών Δήμου Ιστιαίας – Αιδηψού | Υποδομές | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | ναι | όχι |  |  | όχι | όχι
A5 | Πρόγραμμα “ΑΠΟΛΗΨΙΣ” | Δάσος | Πράσινο Ταμείο | ναι | ναι | ναι |  |  | ναι | ναι
A6 | Αποκατάσταση υποδομών σε χώρους δασικής αναψυχής | Δάσος | Πράσινο Ταμείο | ναι | ναι | ναι |  |  | ναι | ναι
A7 | Συντήρηση, Σήμανση & Ανάδειξη σηματοδοτημένων πεζοπορικών διαδρομών στην περιοχή του Δήμου Ιστιαίας – Αιδηψού «Τελέθριον Όρος και Όρος Λίχα» | Δάσος | Ταμείο Ανάκαμψης και Ανθεκτικότητας | ναι | ναι | ναι |  |  | όχι | όχι
A8 | Υδρολογική μελέτη ορεινών και πεδινών έργων στην Βόρεια Εύβοια | Δάσος | Περιφερειακό Πρόγραμμα Ανάπτυξης 2021-2025 | ναι | ναι | ναι |  |  | ναι | ναι
A9 | Εθνικό Μονοπάτι 21 στην Εύβοια | Δάσος | Ταμείο Ανάκαμψης και Ανθεκτικότητας | ναι | ναι | ναι |  |  | όχι | όχι
A10 | Πρόγραμμα Μη Δημόσιας Δασοπονίας | Δάσος | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A11 | Κατασκευή έργων αποκατάστασης των υποδομών του Δασικού χωριού Παπάδων που καταστράφηκαν από την πυρκαγιά στις 3/8/2021 | Δάσος | Εθνικό Πρόγραμμα Ανάπτυξης 2021-2025 | ναι | ναι | ναι |  |  | ναι | ναι
A12 | Πρόγραμμα “ΠΡΟΛΗΨΙΣ”: Προστασία του Δάσους – Έκθεση Επιτροπής Goldammer – Δράση κινητοποίησης τοπικων κοινωνιών | Δάσος | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A13 | “ΕΡΓΟ: Οικονομία του Δάσους – Προστασία και αξιοποίηση προϊόντων και υπηρεσιών των ελληνικών δασών, με διακριτικό τίτλο «ΒΙΩΣΙΜΟΣ ΚΑΘΑΡΙΣΜΟΣ». Υποέργο 1: Ίδρυση Πρότυπης Δασικής Κοιν.Σ.Επ. Β. Εύβοιας «ΑΕΙΦΟΡΙΑ»” | Δάσος | Χορηγίες | ναι | ναι | ναι |  |  | ναι | όχι
A14 | “ΕΡΓΟ: Οικονομία του Δάσους – Προστασία και αξιοποίηση προϊόντων και υπηρεσιών των ελληνικών δασών, με διακριτικό τίτλο «ΒΙΩΣΙΜΟΣ ΚΑΘΑΡΙΣΜΟΣ». Υποέργο 2. Οικονομία του Δάσους – Προστασία ελληνικών δασών και αξιοποίηση δασικών προϊόντων” | Δάσος | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A15 | “Αναδάσωση – Α.Π.Θ. – Αρθρωτή Κυλιόμενη Δράση με την παρακάτω εκδοχή : Σπόροι, Φυτώρια/Φυτάρια, Αναδάσωση, Φυσική Αναγέννηση / Συνεχής Παρακολούθηση, Νερό, Απορρόφηση CO2 Έργο Α. Συλλογή και χειρισμός δασικού αναπαραγωγικού υλικού” | Δάσος | Ταμείο Ανάκαμψης και Ανθεκτικότητας | ναι | ναι | ναι |  |  | ναι | ναι
A16 | “Αναδάσωση – Α.Π.Θ. – Αρθρωτή Κυλιόμενη Δράση με την παρακάτω εκδοχή : Σπόροι, Φυτώρια/Φυτάρια, Αναδάσωση, Φυσική Αναγέννηση / Συνεχής Παρακολούθηση, Νερό, Απορρόφηση CO2 Έργο Β. Παραγωγή φυταρίων στο φυτώριο για την αναδάσωση” | Δάσος | Ταμείο Ανάκαμψης και Ανθεκτικότητας | ναι | ναι | ναι |  |  | ναι | όχι
A17 | “Αναδάσωση – Α.Π.Θ. – Αρθρωτή Κυλιόμενη Δράση με την παρακάτω εκδοχή : Σπόροι, Φυτώρια/Φυτάρια, Αναδάσωση, Φυσική Αναγέννηση / Συνεχής Παρακολούθηση, Νερό, Απορρόφηση CO2 Έργο Γ. Παρακολούθηση της φυσικής αναγέννησης του Νέου Δάσους” | Δάσος | Χορηγίες | ναι | ναι | ναι |  |  | ναι | όχι
A18 | “Αναδάσωση – Α.Π.Θ. – Αρθρωτή Κυλιόμενη Δράση με την παρακάτω εκδοχή : Σπόροι, Φυτώρια/Φυτάρια, Αναδάσωση, Φυσική Αναγέννηση / Συνεχής Παρακολούθηση, Νερό, Απορρόφηση CO2 Έργο Δ. Αναδάσωση – Βιώσιμη Διαχείριση – Βιώσιμος Καθαρισμός” | Δάσος | Ταμείο Ανάκαμψης και Ανθεκτικότητας | ναι | ναι | ναι |  |  | ναι | όχι
A19 | “Αναδάσωση – Α.Π.Θ. – Αρθρωτή Κυλιόμενη Δράση με την παρακάτω εκδοχή: Σπόροι, Φυτώρια/Φυτάρια, Αναδάσωση, Φυσική Αναγέννηση / Συνεχής Παρακολούθηση, Νερό, Απορρόφηση CO2 Έργο Ε. Έργα αποκατάστασης υγρασίας εδάφους (Νερό)” | Δάσος | Άλλοι Πόροι | ναι | ναι | ναι |  |  | όχι | όχι
A20 | “Αναδάσωση – Α.Π.Θ. – Αρθρωτή Κυλιόμενη Δράση με την παρακάτω εκδοχή : Σπόροι, Φυτώρια/Φυτάρια, Αναδάσωση, Φυσική Αναγέννηση / Συνεχής Παρακολούθηση, Νερό, Απορρόφηση CO2 Έργο ΣΤ. Υπολογισμός παρακολούθησης CO2 και αποθήκευσης άνθρακα” | Δάσος | Χορηγίες | ναι | ναι | ναι |  |  | όχι | όχι
A21 | Δράσεις επιμόρφωσης και κατάρτισης τοπικού πληθυσμού | Αγροδιατροφή | Χορηγίες | ναι | ναι | ναι |  |  | ναι | ναι
A22 | Επιμόρφωση Εργαζομένων στον τομέα της εστίασης και αναψυχής | Αγροδιατροφή | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A23 | Αλυσίδες Εφοδιασμού | Αγροδιατροφή | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | όχι | όχι |  |  | όχι | όχι
A24 | Ανοιχτό Ράφι | Αγροδιατροφή | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | όχι | όχι |  |  | όχι | όχι
B2 | Επενδύω στην Β. Εύβοια – Στήριξη υφιστάμενων μικρών και πολύ μικρών επιχειρήσεων της αγροδιατροφικής αλυσίδας στη Βόρεια Εύβοια | Αγροδιατροφή | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | ναι | όχι |  |  | όχι | όχι
A25 | Υποστήριξη κτηνοτροφίας – Κτηνοτροφικές Εγκαταστάσεις | Αγροδιατροφή | Πρόγραμμα Αγροτικής Ανάπτυξης | ναι | όχι | όχι |  |  | όχι | όχι
A26 | Μελισσοκομική Σχολή Ιστιαίας / Σεμινάρια μελισσοκομίας | Αγροδιατροφή | Τομεακό Πρόγραμμα Ανάπτυξης ΥΠΑΙΘ 2021-2025 | ναι | όχι | όχι |  |  | όχι | όχι
A27 | Εγκατάσταση συστήματος ευφυούς γεωργίας στον συνεταιρισμό των Ροβιών | Αγροδιατροφή | Περιφερειακό Πρόγραμμα Ανάπτυξης 2021-2025 | ναι | ναι | ναι |  |  | ναι | ναι
A28 | Δημιουργία Πρότυπων Δημόσιων Δασικών Μελισσοκομείων | Αγροδιατροφή | Χορηγίες | ναι | ναι | ναι |  |  | ναι | ναι
A29 | Έκθεση αγροτικών προϊόντων Βόρειας Εύβοιας – Μετρό Συντάγματος | Αγροδιατροφή | Χορηγίες | ναι | ναι | ναι |  |  | ναι | ναι
A30 | Επιχορήγηση υφιστάμενων επιχειρήσεων που έχουν πληγεί από την πανδημία, σε περιοχές που υπέστησαν μεγάλες φυσικές καταστροφές | Ανθρώπινο Δυναμικό | Πρόγραμμα Ανταγωνιστικότητα 2021-2027 | ναι | ναι | ναι |  |  | ναι | ναι
A31 | Ειδικό πρόγραμμα απασχόλησης α) ρητινεργατών και β) πτυχιούχων ανώτατων εκπαιδευτικών ιδρυμάτων Πανεπιστημιακού και Τεχνολογικού Τομέα σε Υπηρεσίες του Υπουργείου Περιβάλλοντος και Ενέργειας | Ανθρώπινο Δυναμικό | ΔΥΠΑ | ναι | ναι | ναι |  |  | ναι | όχι
A32 | Πρόγραμμα προεργασίας για 300 ανέργους νέους, ηλικίας 18-30 σε επιχειρήσεις του ιδιωτικού τομέα και σε επιχειρήσεις, φορείς, οργανισμούς του δημοσίου τομέα που ασκούν τακτικά οικονομική δραστηριότητα, στους Δήμους Ιστιαίας-Αιδηψού και Μαντουδίου – Λίμνης – Αγίας Άννας, της Περιφερειακής Ενότητας Ευβοίας. | Ανθρώπινο Δυναμικό | ΔΥΠΑ | ναι | ναι | ναι |  |  | ναι | ναι
A33 | Υποδομές Προγράμματος POLITIS:Δημιουργία ενός Κέντρου Χωροταξίας και Περιβάλλοντος (ΚΕΧΩΠ), ενός ολιστικού πολυδύναμου Κέντρου Εξυπηρέτησης Πολιτών (ΚΕΠ) και ενός χώρου για τον Διαδημοτικό Αναπτυξιακό Οργανισμό (DMO) στην Ιστιαία, καθώς και ενός νέου ΚΕΠ με Κοινοτικό Ιατρείο στον οικισμό Βασιλικών. | Ανθρώπινο Δυναμικό | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A34 | Υποδομές Προγράμματος POLITIS:Δημιουργία ενός Κέντρου Εξυπηρέτησης Πολιτών (ΚΕΠ) και ενός Κέντρου Χωροταξίας και Περιβάλλοντος (ΚΕΧΩΠ) στο Μαντούδι, καθώς και ενός ΚΕΠ στον οικισμό Αγίας Άννας. | Ανθρώπινο Δυναμικό | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A35 | Ψηφιακές Εφαρμογές Πρόγραμμα «ΠΟΛΙΤΗΣ» (Αναβάθμιση Πληροφοριακού Συστήματος Κ.Ε.Π.) | Ανθρώπινο Δυναμικό | Χρηστή Διακυβέρνηση - Θεσμοί και Διαφάνεια / ΧΜ-ΕΟΧ (EEA Grants) 2014–2021 | ναι | ναι | ναι |  |  | ναι | ναι
A36 | Ψηφιακές Εφαρμογές Πρόγραμμα «ΠΟΛΙΤΗΣ» (Γεωπύλη Γεωχωρικών Πληροφοριών των Δήμων και Κωδικοποίηση της περιβαλλοντικής νομοθεσίας – Δήμος Αιδηψού) | Ανθρώπινο Δυναμικό | Χορηγίες | ναι | όχι | όχι |  |  | όχι | όχι
A37 | Ψηφιακές Εφαρμογές Πρόγραμμα «ΠΟΛΙΤΗΣ» (Γεωπύλη Γεωχωρικών Πληροφοριών των Δήμων και Κωδικοποίηση της περιβαλλοντικής νομοθεσίας – Δήμος Λίμνης) | Ανθρώπινο Δυναμικό | Χορηγίες | ναι | όχι | όχι |  |  | όχι | όχι
A38 | Ψηφιακές Εφαρμογές Πρόγραμμα «ΠΟΛΙΤΗΣ» (Ψηφιακό Παρατηρητήριο Βιώσιμης Τουριστικής Ανάπτυξης DataHub) Δήμος Ιστιαίας | Ανθρώπινο Δυναμικό | Χορηγίες | ναι | όχι | όχι |  |  | όχι | όχι
A39 | Μελέτη Ίδρυσης Ενεργειακής Κοινότητας των Δήμων Μαντουδίου – Λίμνης – Αγ. Άννας και Ιστιαίας – Αιδηψού | Ανθρώπινο Δυναμικό | Πράσινο Ταμείο | ναι | ναι | ναι |  |  | ναι | όχι
A40 | Προμήθεια ενός (1) Ασθενοφόρου Οχήματος (4×4) για τις ανάγκες του Κέντρου Υγείας Ιστιαίας | Υγεία & Πρόνοια | Εθνικό Πρόγραμμα Ανάπτυξης 2021-2025 | ναι | ναι | ναι |  |  | όχι | όχι
A41 | Προμήθεια Ιατροτεχνολογικού Εξοπλισμού για τις Ανάγκες του ΚΥ Ιστιαίας (Περιλαμβάνει κέντρο Χρόνιων Ασθενών) | Υγεία & Πρόνοια | Εθνικό Πρόγραμμα Ανάπτυξης 2021-2025 | ναι | ναι | ναι |  |  | ναι | όχι
A42 | Προμήθεια Ιατροτεχνολογικού Εξοπλισμού για τις Ανάγκες του ΚΥ Μαντουδίου | Υγεία & Πρόνοια | Εθνικό Πρόγραμμα Ανάπτυξης 2021-2025 | ναι | ναι | ναι |  |  | ναι | ναι
A43 | Προμήθεια 1 Κινητής Γυναικολογικής Μονάδας για τις Ανάγκες του Πληθυσμού της Βόρειας Εύβοιας | Υγεία & Πρόνοια | Εθνικό Πρόγραμμα Ανάπτυξης 2021-2025 | ναι | ναι | ναι |  |  | ναι | όχι
A44 | Προμήθεια 1 Κινητής Μονάδας Αιμοληψίας | Υγεία & Πρόνοια | Εθνικό Πρόγραμμα Ανάπτυξης 2021-2025 | ναι | ναι | ναι |  |  | ναι | όχι
A45 | Προληπτική Ιατρική – Δράσεις Προβολής και Ενημέρωσης σε διάφορα σημεία της Βόρειας Εύβοιας, | Υγεία & Πρόνοια | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A46 | Τηλεσυμβουλευτική – Πιλοτική εφαρμογή της υπάρχουσας ανενεργής πλατφόρμας για τις θεματικές: α) Covid, β) Ψυχική Υγεία παιδιών και εφήβων και επέκταση της για την Φροντίδα Χρόνιων Ασθενών & Προσωπικό Ιατρό | Υγεία & Πρόνοια | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A47 | Δημιουργία Χάρτας Αναγκών για τα δίκτυα υγείας και πρόνοιας στο Πλαίσιο της Ανασυγκρότησης της Βόρειας Εύβοιας | Υγεία & Πρόνοια | Χορηγίες | ναι | ναι | ναι |  |  | ναι | ναι
B3 | Ενίσχυση της κοινωνικής μέριμνας, προστασίας και συμπερίληψης: «Πρώτη Αγκαλιά» | Υγεία & Πρόνοια | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | ναι | όχι |  |  | όχι | όχι
B4 | Ενίσχυση της κοινωνικής μέριμνας, προστασίας και συμπερίληψης: Βιωματικά Εργαστήρια Πολιτισμού για Εφήβους | Υγεία & Πρόνοια | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | ναι | όχι |  |  | όχι | όχι
B5 | Αυτόνομη διαβίωση ατόμων που έχουν ανάγκη στη Βόρεια Εύβοια | Υγεία & Πρόνοια | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | ναι | όχι |  |  | όχι | όχι
A48 | ΕΡΓΟ: Επαναλειτουργία του Υδροθεραπευτηρίου Λουτρών Αιδηψού ΥΠΟΕΡΓΟ 3: Διαχείριση και Διανομή Ιαματικού Πόρου του Κέντρου Ιαματικού Τουρισμού / Θερμαλισμού Αιδηψού | Τουριστική Ανάπτυξη | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A49 | Τουριστική Προβολή | Τουριστική Ανάπτυξη | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A50 | Εγκατάσταση δωρεάν Wifi σημείων στους Δήμους Β. Εύβοιας | Τουριστική Ανάπτυξη | Χορηγίες | ναι | ναι | ναι |  |  | ναι | ναι
AB51 | Αναβάθμιση Τουριστικών Πόλων / Παραλία Αγ. Άννας | Τουριστική Ανάπτυξη | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | ναι | όχι |  |  | όχι | όχι
AB52 | Αναβάθμιση Τουριστικών Πόλων / Παραλία Ροβιών | Τουριστική Ανάπτυξη | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | ναι | όχι |  |  | όχι | όχι
A53 | Γαλάζιες Σημαίες | Τουριστική Ανάπτυξη | ΟΦΥΠΕΚΑ | ναι | ναι | ναι |  |  | όχι | όχι
A54 | Εκπαίδευση – Κατάρτιση – Υποστήριξη επαγγελματιών τουρισμού και τοπικού πληθυσμού | Τουριστική Ανάπτυξη | Πρόγραμμα Ανταγωνιστικότητα 2021-2027 | ναι | όχι | όχι |  |  | όχι | όχι
A55 | ΕΡΓΟ: Επαναλειτουργία του Υδροθεραπευτηρίου Λουτρών Αιδηψού ΥΠΟΕΡΓΟ 2: Ανάπλαση περιβάλλοντος Χώρου | Τουριστική Ανάπτυξη | Άλλοι Πόροι | ναι | ναι | ναι |  |  | ναι | όχι
A56 | Μουσειακή Έκθεση στους Ωρεούς | Πολιτισμός | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | όχι | όχι |  |  | όχι | όχι
B6 | Κέντρο Ιστορικής Ενημέρωσης / Εκθεσιακός χώρος Ωρεών | Πολιτισμός | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027 | ναι | ναι | όχι |  |  | όχι | όχι
A57 | Απολιθωμένο Δάσος – Παράρτημα Κερασιάς | Πολιτισμός | Πράσινο Ταμείο | ναι | ναι | ναι |  |  | ναι | όχι
A58 | Κτήριο Αγίων Αναργύρων – Μουσείο Βόρειας Εύβοιας | Πολιτισμός | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A59 | Ανασκαφική έρευνα στο Καστρί Κηρίνθου | Πολιτισμός | Εθνικό Πρόγραμμα Ανάπτυξης 2021-2025 | ναι | ναι | ναι |  |  | ναι | όχι
A60 | Αποκατάσταση του Ιστορικού Διατηρητέου Μνημείου “Κονάκι” στις Κεχριές Ευβοίας | Πολιτισμός | ΠΕΚΑ (Πρώην ΥΜΕΠΕΡΑΑ) | ναι | ναι | ναι |  |  | όχι | όχι
A61 | Αποκατάσταση του Ναού των Ταξιαρχών στην Κοκκινομηλιά της Βόρειας Εύβοιας | Πολιτισμός | Χορηγίες | ναι | ναι | ναι |  |  | ναι | όχι
A62 | Δίκτυα Αρχιτεκτονικής Κληρονομιάς Βόρειας Εύβοιας | Πολιτισμός | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A63 | Δημιουργία Κινηματογραφικού Πόλου Ανταλλαγής Ιδεών και Αγοράς Ταινιών με επίκεντρο το Περιβάλλον με τον τίτλο «Εvia Film Project». ΦΕΣΤΙΒΑΛ ΚΙΝΗΜΑΤΟΓΡΑΦΟΥ ΘΕΣΣΑΛΟΝΙΚΗΣ | Πολιτισμός |  | ναι | ναι | ναι |  |  | ναι | ναι
A64 | Εκπαιδευτική, Καλλιτεχνική και Περιβαλλοντική δράση σε 2 επιλεγμένες περιοχές της Εύβοιας ΕΘΝΙΚΗ ΛΥΡΙΚΗ ΣΚΗΝΗ | Πολιτισμός |  | ναι | ναι | ναι |  |  | ναι | ναι
A65 | Οι Γέφυρες της μουσικής ΜΕΓΑΡΟ ΜΟΥΣΙΚΗΣ ΑΘΗΝΩΝ | Πολιτισμός |  | ναι | ναι | ναι |  |  | ναι | ναι
A66 | Πολιτιστικά και αθλητικά δρώμενα – Τοπικό πολιτιστικό κεφάλαιο | Πολιτισμός | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A67 | Εκπαιδευτικό Πρόγραμμα «ΣτηρίΖΟΥΜΕ Βόρεια Εύβοια» | Πολιτισμός | Εθνικό Πρόγραμμα Ανάπτυξης 2021-2025 | ναι | ναι | ναι |  |  | ναι | ναι
A68 | Γιορτές του Δάσους | Πολιτισμός | Άλλοι Πόροι | ναι | ναι | ναι |  |  | ναι | ναι
A69 | Κατάρτιση – ευαισθητοποίηση – εμψύχωση επαγγελματιών & τοπικού πληθυσμού | Πολιτισμός | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A70 | Σχεδίαση και Ανάπτυξη Καινοτόμων Ψηφιακών Τεχνολογικών Υποδομών και Υπηρεσιών για την Ανασυγκρότηση της Βόρειας Εύβοιας | Οριζόντια Τεχνικά Δελτία | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι
A71 | Συμβουλευτική, Κατάρτιση και Πιστοποίηση Ανθρώπινου Δυναμικού Βόρειας Εύβοιας | Οριζόντια Τεχνικά Δελτία | Άλλοι Πόροι | ναι | όχι | όχι |  |  | όχι | όχι

## Lists
Categories_EN | Categories_GR | Funders_EN | Funders_GR | Status_EN | Status_GR
Infrastructure | Υποδομές | Other | Άλλοι Πόροι | yes | ναι
Forest | Δάσος | National Employment Service (Δ.ΥΠ.Α) | Δ.ΥΠ.Α. | no | όχι
Agrifood sector | Αγροδιατροφή | National Infrastructure Development Programme | Εθνικό Πρόγραμμα Ανάπτυξης (ΕΠΑ) Υποδομών | unknown | άγνωστο
Human Resources | Ανθρώπινο Δυναμικό | National Development Programme 2021-2025 | Εθνικό Πρόγραμμα Ανάπτυξης 2021-2025
Healthcare & Welfare | Υγεία & Πρόνοια | Natural Environment & Climate Change Organization | Οργανισμός Φυσικού Περιβάλλοντος & Κλιματικής Αλλαγής (O.ΦΥ.ΠΕ.Κ.Α.)
Tourism | Τουριστική Ανάπτυξη | Programme Environment & Climate Change | Πρόγραμμα Περιβάλλον & Κλιματική Αλλαγή (ΠΕ.Κ.Α.)
Culture | Πολιτισμός | Regional Operational Program of Sterea Ellada 2014-2020 (ΠΕΠ 2014-2020) | ΠΕΠ «Στερεά Ελλάδα 2014-2020»
General | Οριζόντια Τεχνικά Δελτία | Regional Development Program 2021-2025 | Περιφερειακό Πρόγραμμα Ανάπτυξης 2021-2025
|  | Green Fund | Πράσινο Ταμείο
|  | Regional Program of Sterea Ellada 2021-2027 | Πρόγραμμα «Στερεά Ελλάδα» 2021-2027
|  | Rural Development Programme | Πρόγραμμα Αγροτικής Ανάπτυξης
|  | Competitiveness 2021–2027 Programme | Πρόγραμμα Ανταγωνιστικότητα 2021-2027
|  | Recovery & Resilience Plan | Ταμείο Ανάκαμψης και Ανθεκτικότητας
|  | Sectoral Development Program of the Ministry of Education 2021-2025 | Τομεακό Πρόγραμμα Ανάπτυξης ΥΠΑΙΘ 2021-2025
|  | Donations | Χορηγίες
|  | Good Governance - Institutions and Transparency'_ European Economic Area Grants 2014-2021 | Χρηστή Διακυβέρνηση - Θεσμοί και Διαφάνεια / ΧΜ-ΕΟΧ (EEA Grants) 2014–2021
Not defined
Diazoma